## Project Schedule LOJA
PROJECT SCHEDULE
PROJECT NAME |  |  |  |  | START DATE
BELLA BOUTIQUE | E-COMMERC |  |  |  | 2024-03-30
PROJECT MANAGER |  |  |  |  | END DATE
2024-04-15
| TIMELINE |  |  |  | PROJECT NOTES
PHASE TITLE | HOUR | START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
PESQUISA EXPLORATÓRIA | 5 | 2024-03-30 | 2024-04-02 | 4
REQUISITOS FUNCIONAIS E NÃO FUNCIONAIS | 5 | 2024-03-30 | 2024-04-02 | 4
REGRAS DE NEGÓCIO | 3 | 2024-04-03 | 2024-04-04 | 2
USE CASE | 3 | 2024-04-04 | 2024-04-04 | 1
MODELAGEM DE DADOS | 6 | 2024-04-05 | 2024-04-07 | 3
REVISÃO | 8 | 2024-04-08 | 2024-04-09 | 2 | SUBIR VERSÃO
SUBIR VERSÃO | 1 | 2024-04-10 | 2024-04-10 | 1 | SUBIR VERSÃO
INSERIR DADOS MARCA, COR TAM,CATEG,SUBC | 2 | 2024-04-11 | 2024-04-11 | 1
INSERIR DADOS | 2 | 2024-04-12 | 2024-04-12 | 1
INSERIR DADOS | 2 |  |  | 1
1
1
1
1
DELIVERY TIMELINE
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Modelo conceitual: - Pesquisa exploratória - Identificação de problema - Requisitos funcionais e não funcionais - Regras de Negócio
-
Modelo lógico: - Entidades - Atributos - Relacionamentos
Modelagem de dados